## Sheet1
Name of Procuring Entity: |  | EXPLORATION INVESTMENT COMPANY BOTSWANA
Name of Person(s) Responsible For Procurement: | [5 empty] | Contact Tel.
Project Code/ Vote | Project Name | Budget Amount | Activity Name | Procurement Method PPRA Reg. 55-61 | Descipline | Estimated Cost | Preparation of ITT | Submission of ITT for Vetting POU | Publication Date | Invitation Date | Tender Close Date PPRA Reg. 33 | Evaluation completion by PE | Verification of Evaluation report by PU | Submission of evaluation report to POU | Pre-Adjudication by POU | Award Decision | Cooling-Off Period | Contract Signing | Project Commencement | Project Completion | Activity Report
|  | In Numbers |  | ODB;OIB;RDB;RIB;DP;QPM | Goods; Services; Works | In Numbers | DD-MM-YY format | DD-MM-YY format | DD-MM-YY format | DD-MM-YY format | DD-MM-YY format | DD-MM-YY format | DD-MM-YY format | DD-MM-YY format | DD-MM-YY format | DD-MM-YY format | DD-MM-YY format | DD-MM-YY format | DD-MM-YY format | DD-MM-YY format | DD-MM-YY format
INFORMATION TECHNOLOGY/INFORMATION SYSTEMS
IT/IS | Internet and Communication | 60000 | Hosted communication solution (BTC) | DP | Services | 60000 | 2026-05-05 | 2026-05-07
IT/IS | Information Systems | 102000 | M365 business premium solution(email, collaboration) | Request for Quotation | Services | 100000 | 2026-05-05 | 2026-05-07
IT/IS | Information Systems | 45000 | Teamwork project management platform | Request for Quotation | Services | 45000 | 2026-05-05 | 2026-05-07
IT/IS | Information Systems | 65000 | Adobe sign solution | Request for Quotation | Services | 65000 | 2026-05-05 | 2026-05-07
IT/IS | Business Communications | 700000 | End-User Computing Devices /laptops | Open Domestic Bidding | Supplies | 700000 | 2026-05-25 | 2026-06-01 | 2026-06-10 | 2026-06-10 | 2026-06-23
IT/IS | Information Systems | 3000000 | Exploration Data and information review, modelling and AI enablement | International Restrictive Bidding | Services | 3000000 | 2026-05-29 | 2026-06-02 | 2026-06-10 | 2026-06-10 | 2026-07-02
IT/IS | Information Systems | 100000 | Cybersecurity and identity management | Open Domestic Bidding | Services | 100000 | 13/07/2026 | 15/07/2026
IT/IS | Information Systems | 1000000 | Enterprise Resource planning software (Finance, Procurement, HR) | Open Domestic Bidding | Services | 1000000 | 19/05/2026 | 20/05/2026
IT/IS | Information Systems | 40000 | Network & Connectivity | Request for Quotation | Services | 40000 | 22/07/2026 | 24/07/2026
IT/IS | Information Systems | 50000 | Backup, Recovery & Business Continuity | Request for Quotation | Services | 50000 | 22/07/2027 | 24/07/2027
IT/IS | Information Technology | 1000000 | IT Hardware and peripherals | Request for Quotation | Supplies | 1000000 | 22/07/2028 | 24/07/2028
IT/IS | Information Systems | 193000 | Geoscience data analysis Software and training | Direct Procurement | Services | 190000 | 22/07/2029 | 24/07/2029
IT/IS | Information Systems |  | Freshservice service desk | Request for Quotation | Services | 0 | 22/07/2030 | 24/07/2030
IT/IS | Information Technology | 180000 | Printer Rental | Open Domestic Bidding | Services | 180000 | 22/07/2031 | 24/07/2031
TOTAL | [5 empty] | 6530000
HUMAN RESOURCES
HR | Courier & Postage | 2000 | Courier charges | Open Domestic Bidding | Services | 2000
HR | Subscriptions | 6120 | DSTV Subscription | Open Domestic Bidding | Services | 6000
HR | Security | 4860 | Alarm monitoring | Quotations/Proposals | Services | 5000
HR | Insurance | 150000 | Group life insurance | Open Domestic Bidding | Services | 150000
HR | Recreational Expenses | 30000 | Staff Gym membership | Open Domestic Bidding | Services | 30000
HR | Professional bodies | 50000 | Professional memberships | Direct Procurement | Services | 50000
HR | Annual HR Surveys | 200000 | Implemetation of the Remuneration frmework (Pay Progression Model, grading of JDs) | Open Domestic Bidding | Services | 200000
HR | consultancy other | 50000 | HR Consultancy Services | Open Domestic Bidding | Services | 50000
HR | Recruitment | 215000 | Recruitment cost | Open Domestic Bidding | Services | 200000
HR | Workshops and Retreats | 500000 | Workshops, Seminars, Conferences, Short training | Open Domestic Bidding | Services | 500000
HR | HRIS Solutions | 500000 | HRIS Solutions | Direct Procurement | Services | 500000
HR | consultancy other | 350000 | PMS training, workshops and cascading of departmental scorecard and cascade solution annual lisence, PMS automation | Open Domestic Bidding | Services | 350000
HR | International travel, Accommdation and Meals | 300000 | Travel - Accomodation, meals and sundires | Quotations/Proposals | Services | 300000
HR |  | 650000 | Implementation of Data Protection Act | Open Domestic Bidding | Services | 650000
HR | CAPEX | 270000 | Medical Aid Services | Local Restrictive Bidding | Services | 270000 | 10.06.2026 | 13.06.2026 | 16.06.2026 | 16.06.2026 | 26.06.2026
TOTAL | [5 empty] | 3263000
ADMINISTRATION
ADM | Administration | 840000 | Office rental | Direct Procurement | Services | 840000 | 01.04.2026 | 01.04.2026 | 03.04.2026 | 06.04.2026 | 10.04.2026 | 13.04.2026 | 16.04.2026 | 16.04.2026 | 17.04.2026 | 17.04.2026 | 01.05.2026 | 04.05.2026 | 05.05.2026 | 31.12.2026 | 01.01.2027
ADM | Administration | 3000000 | Supply, delivery and Registration of Vehicles | Direct Procurement | Supplies | 3000000 | 15.06.2026 | 16.06.2026 | 16.06.2026 | 16.06.2026 | 26.06.2026 | 30.06.2026 | 01.07.2026 | 01.07.2026 | 05.07.2026 | 05.07.2026 | 22/07/2026 | 24/07/2026 | 24/07/2026 | 03.08.2026 | 03.08.2026
ADM | Administration | 100000 | Business communication services on a 12 month contract | Direct Procurement | Services | 100000 | 20.07.2026 | 21.07.2026 | 23.07.2026 | 2026-08-01 | 02.08.2026 | 2026-08-15 | 16.08.2026 | 2026-09-01 | 15.09.2026 | 16.09.2026 | 2026-10-05 | 01.11.2026 | 02.11.2026 | 31.12.2026 | 01.01.2027
ADM | Administration | 100000 | Office Consumables | Request for Quotation | Supplies | 100000 | 01.06.2026 | 25/06.2026 | 30.06.2026 | 2026-07-01 | 2026-07-21 | 2026-08-01 | 02.08.2026 | 2026-08-15 | 16.08.2026 | 2026-09-01 | 15.09.2026 | 16.09.2026 | 2026-10-05 | 01.11.2026 | 02.11.2026
ADM | Administration | 300000 | Office Equipment, Interactive screen, Office furniture | Request for Quotation | Supplies | 300000 | 15.06.2026 | 25/06.2026 | 30.06.2026 | 2026-07-01 | 2026-07-21 | 2026-08-01 | 02.08.2026 | 2026-08-15 | 16.08.2026 | 2026-09-01 | 15.09.2026 | 16.09.2026 | 2026-10-05 | 01.11.2026 | 02.11.2026
ADM | Administration | 100000 | Stationery | Request for Quotation | Supplies | 100000 | 15.06.2026 | 25/06.2026 | 30.06.2026 | 2026-07-01 | 2026-07-21 | 2026-08-01 | 02.08.2026 | 2026-08-15 | 16.08.2026 | 2026-09-01 | 15.09.2026 | 16.09.2026 | 2026-10-05 | 01.11.2026 | 02.11.2026
ADM | Administration | 50000 | Asset insurance | Open Domestic Bidding | Services | 50000 | 01.06.2026 | 25/06.2026 | 30.06.2026 | 2026-07-01 | 2026-07-21 | 2026-08-01 | 02.08.2026 | 2026-08-15 | 16.08.2026 | 2026-09-01 | 15.09.2026 | 16.09.2026 | 2026-10-05 | 01.11.2026 | 02.11.2026
ADM | Administration | 100000 | Vehicle repairs, services and maintenance | Open Domestic Bidding | Services | 100000 | 03.08.2026 | 04.08.2026 | 06.08.2026 | 2026-08-15 | 16.08.2026 | 18.08.2026 | 19.08.2026 | 20.08.2026 | 20.08.2026 | 21.08.2026 | 2026-09-01 | 15.09.2026 | 16.09.2026 | 2026-10-05 | 01.11.2026
ADM | Administration | 100000 | Fuel supply | Open Domestic Bidding | Services | 100000 | 03.08.2026 | 04.08.2026 | 06.08.2026 | 2026-08-15 | 16.08.2026 | 18.08.2026 | 19.08.2026 | 20.08.2026 | 20.08.2026 | 21.08.2026 | 2026-09-01 | 15.09.2026 | 16.09.2026 | 2026-10-05 | 01.11.2026
ADM | Administration | 250000 | Office Maintenance and repairs | Request for Quotation | Works | 250000 | 03.08.2026 | 04.08.2026 | 06.08.2026 | 2026-08-15 | 16.08.2026 | 18.08.2026 | 19.08.2026 | 20.08.2026 | 20.08.2026 | 21.08.2026 | 2026-09-01 | 15.09.2026 | 16.09.2026 | 2026-10-05 | 01.11.2026
ADM | Administration | 50000 | Fleet tracking | Open Domestic Bidding | Services | 50000 | 03.08.2026 | 04.08.2026 | 06.08.2026 | 2026-08-15 | 16.08.2026 | 18.08.2026 | 19.08.2026 | 20.08.2026 | 20.08.2026 | 21.08.2026 | 2026-09-01 | 15.09.2026 | 16.09.2026 | 2026-10-05 | 01.11.2026
TOTAL | [5 empty] | 4150000
TECHNICAL
TECH | Field Equipment | 700000 | Field Equipment | Request for Quotation | Supplies | 700000 | 15.06.2026 | 25/06.2026 | 30.06.2026 | 2026-07-01 | 2026-07-21 | 2026-08-01 | 02.08.2026 | 2026-08-15 | 16.08.2026 | 2026-09-01 | 15.09.2026 | 16.09.2026 | 2026-10-05 | 01.11.2026 | 02.11.2026
TECH | Training and Development | 300000 | Investing in Africa Mining Indaba | Direct Procurement | Services | 300000
TECH | Field Equipment | 100000 | Personal And Protective Equipment | Open Domestic Bidding | Supplies | 100000 | 08.06.2026
TECH | [5 empty] | 0
TOTAL | [5 empty] | 1100000
MARKETING AND COMMUNICATIONS
MARC | Corporate identity | 70000 | Publications (Annual Report) | Request for Quotation | Supplies | 70000 | 20.03.2027 | 30.03.2027 | 31.03.2027 | 01.04.2027 | 21.04.2027 | 2027-04-26 | 10.04.2026 | 13.04.2026 | 16.04.2026 | 16.04.2026 |  |  | 01.05.2026 | 04.05.2026
MARC | Corporate identity | 350000 | Corporate Marketing and Advertising | Request for Quotation | Services | 350000 | As needed | As needed | As needed | As needed | As needed | As needed | As needed | As needed | As needed | As needed | As needed | As needed | As needed | As needed | As needed
MARC | Corporate identity | 100000 | Corporate Events (Internal) | Request for Quotation | Services | 100000 | As needed | As needed | As needed | As needed | As needed | As needed | As needed | As needed | As needed | As needed | As needed | As needed | As needed | As needed | As needed
MARC | Corporate identity | 600000 | Corporate Events (External) | Request for Quotation | Services | 600000 | As needed | As needed | As needed | As needed | As needed | As needed | As needed | As needed | As needed | As needed | As needed | As needed | As needed | As needed | As needed
MARC | Corporate identity | 250000 | Corporate Identity | Direct Procurement | Services | 250000 | 01.02.2026 | 25/02.2026 | 30.02.2026 | As needed | As needed | As needed | As needed | As needed | As needed | As needed | As needed | 2026-03-01 | 2026-03-01 | 01.07.2026 | As needed
MARC | Corporate identity | 300000 | Merchandise & Branding | Request for Quotation | Supplies | 300000 | As needed | As needed | As needed | As needed | As needed | As needed | As needed | As needed | As needed | As needed | As needed | As needed | As needed | As needed | As needed
MARC | [5 empty] | 0
TOTAL | [5 empty] | 1670000
STRATEGY AND BUSINESS DEVELOPMENT
BD | Strategy | 3000000 | Development of the Investment Model Framework | Restrictive International Bidding | Services | 3000000
BD | Strategy | 1500000 | Strategy development | Open Domestic Bidding | Services | 1500000
BD | Strategy | 1000000 | Strategy Monitoring | Open Domestic Bidding | Services | 1000000
BD | [5 empty] | 0
BD
TOTAL | [5 empty] | 5500000
GRAND-TOTAL | [5 empty] | 20543000